## 3 Year Planning Framework
Anticipated Duration (Months)	1	1					1	0.5	0.5	1	1	3.5	6	6	5	1	0.5	Forever	Total =	28	and Forever
	TestLab - Research and Development						PRE MONASTERY					THE CYCLES - unMonastery					deMONASTERY
	Proposition	Stakeholders, Networks and Partnerships	Recruitment	Repairs & Refurb	unMonastery TestLab	TestLab unSummit	Pre-Mon / Recon	Summit	Startup	Uncivilisation Readjustment Therapy	Unopening	6 Months	12 Months	18 Months	24 Months	Unclosing	After Care	Follow Up
Journey	Would it work here?	Who will support, pay and/or help develop the unMonastery in the community?		Remember you'll be living here	Who is taking leadership?	Site-specific gathering to prepare to evaluate the TestLab and decide on further possibilities	Build a team, Go there, Make it Hardcore	Establish Critical Mass. Put it through it's paces --- DDOS THE BUILDING --- Prime the Mortar for action and dicussion	unMon in a box will help you; good luck.	Learn to love and respect each other	Introduce yourselves and pray that people come					Burn success and publicly celebrate your mistakes	You have a responsibility to relationships formed.	Don't break the connection, go back.
TIMELINE	June 2016, Summer Camp/ FOLLOW-UP Visit September 16-18	Slowly building between January 2016-June 2017	Summer 2016 ongoing	Summer 2016-February 2018	July-October 2017	October 2017	Summer 2016 - February 2018	December 2017	February 2018	ongoing	April 2018	July 2018	February 2019	July 2019	February 2020	Summer 2020
COMMON / PUBLIC	Every visit is already an unMonastery visit, use the toolkit to plan daily rhythms and personal behavior.
Key Tasks / Objectives	Establish unMonastery culture: Life rhythms, commitment, moon celebrations, reading, toolkit. Meet with partners & Build relationships: - LOCAL: Taverna, Sakis, Sotiris - SARANTAPORO: community mesh network, Achilleas - ATHENS: George and Vassilis, Ilias Marmadas In the aftermath of the documentary, there is an ongoing interest in the area covered by the community network, and several startups are planning to work with Sarantaporo.gr to develop local business opportunities with the aid of agritech, IoT, etc --- Assess Location and Building According to framework: - LOCATION: advantages: - beautiful area, spritual and mythical background, - quiet country life, enabling unMonasticism to flourish - 13 villages connected by wireless mesh network that is owned by the community - summer camp and school building empty drawback: very remote - BUILDING: - enough space, large stone building with some history - needs a kitchen - winterisation is an issue --- Action Plan for Pre-Unmon Recon - Follow-up visit - Athens meetings - Elassona authorities ---	-Local council (Sakis, Sotiris, etc) -Sarantaporo.gr -Athens startups (Vassilis, George) -University in Larissa -other universities (Athens, Volos) -offline network community -P2P Lab Ioannina - Athens Integral Cooperative	Go headhunting --- Sculpt the call --- Establish unMonk criteria, decision making framework and pick --- Start learning the language	What makes it an unMonastery at all times? -- Repair itThe building is in a state that it is suitable for modest habitation, as long as it is not cold. It needs a kitchen. --- Who's paying?Shared between village and unMonastery. We can ask for donations. Should minimise costs by working on it ourselves. Salvage materials, keep things simple. --- Order & fit unMon starter kit --- Connect utilities	Leading: Katalin and Jeff Remote support: Ben, Kei, Valeria Research Project: - unMonastic life rhythms - offline network pilot preparation: what aspects of unMonastic life can be enhanced by this technology? - long-term sustainability Scale: - small - 5-8 people at a time Sustainability: - offline networks teaching summer camps, agritech startups, - Long term and short term goals of participants - Timeframe - Practicalities and - How to make a living - House rules for guests, - Research Project - Ways to create relationships with local community - Decide on openness (is it possible to join? how?) - Decide on engagement with global unMon network - Ends with topical TestLab (Research) unSummit	- Research Findings - Documentation - Evaluation of possible futures	Assemble Team, Equipment & Materials --- Host two Public Meetings --- Define Objectives --- Catalog in High Detail Building Faults --- Setup Website --- Establish Legals / Paperwork	Synthesise objectives into a meaningful event --- Invite people --- Involve locals	Coordinate Arrival --- Source 1st Project Materials --- Get Kitchen / Food up and running	Alignment --- Agree Strategies --- Adopt Roles	Involve & Invite Locals into organising and participating at the unOpening - CONNECTION with ATHENS (integral cooperative) --- Do the Event - Trust in the Process	- how to make a living - house rules for guests, - how to initiate and join projects, - ways to create relationships with local community, - decide on openness (is it possible to join? how?), - decide on engagement with global unMon network, - Ends with Protocol Summit	- are you making a living? - projects with local community - projects with global network - are you open enough? (is it possible to join? how?) - writing own Book of Mistakes - Ends with bGLO Summit	- ask stakeholders for a review (including invisible stakeholders) - write your own evaluation of these relationships - is there a local partner for each unMonastery project? - re-visit and refine each collaboration's purpose and expectations - local community - inhouse - network - Write the Book of Stakeholders - Ends with Stakeholders Summit	- review the network created around the unMonastery - review captured data (production, consumption, contributions to commons) - evaluate consumption patterns, networks, work (value) created - capture all in visual format (Atlas) - ends with Commons Summit? ---- Start handing over projects to local collaborators Plan & Book return follow up	Schedule 1 week for group assesment of project --- Assign individual unMonks to important allies and friends, so to ensure relationship are maintained --- Plan unClosing	Be sure you leave the building better than you found it and in good clean standing --- Finalise Building Manual --- Manage with care the hand over procedure	Continue to invite energy & network resource into whatever the building has become ---- Send delegation on 6 month cycles, to visit and feast --- Continue remote calls with allies & friends
Communication	Weekly Community Calls						Weekly Community Calls	Weekly Community Calls	Weekly Community Calls			Weekly Calls, Monthly Community Calls	Weekly Calls, Monthly Community Calls	Weekly Calls, Monthly Community Calls	Weekly Calls, Monthly Community Calls
The Work	DELIVERABLE: Scoping Report ---						DELIVERABLE: Building Report & Proposed Fixes --- Building Rituals	DELIVERABLE: Mobilise local networks --- DELIVERABLE: Bring an international conversation and expertise --- Refine, change and delete projects with respect to place.	Deciding existing projects to fork	Establish Routine		Protocol	Book of Mistakes	Book of Stakeholders	Atlas
The Network

BACKSTAGE
Personal Wellbeing									Rescue missions from civilisation - Arrival & Returning
The Building & Utilities	Assess Multiple Buildings --- Research Utilities			Install Open Energy Monitor			Log Building Report & Begin Repairs --- Map Building in 3D --- Photograph building	Structure Hackathon sessions around repairing the building --- Plan first iteration of the layout	Fit unMonk Kits --- Establish a prioritised plan for building improvement & systems --- Finish fitout		Create Map & walk through of unOpening Event	Reassess use of building ---- Maintain Clean Living Standards ---- Continue Improvements ---- Keep track of resources	Reassess use of building ---- Maintain Clean Living Standards ---- Continue Improvements ---- Keep track of resources	Reassess use of building ---- Maintain Clean Living Standards ---- Continue Improvements ---- Keep track of resources	Reassess use of building ---- Maintain Clean Living Standards ---- Continue Improvements ---- Keep track of resources ---- Pay Final Bills		Finanlise Building Log and Manual
unMon in a Box	Scoping Report Framework / Document Template		Application Form --- unMonastery website & network --- Talking Pieces	Building Report --- Building Log & Manual			Building Report Framework --- Building Scoping Kit	LOTE unConference Planner --- Harmonious Hackathon Framework --- Twitterstorm --- unMonastery website & network	Use Card Deck --- Use Wiki --- Read the Book of Mistakes	Read about Sleeping Arrangements	Website --- Poster & Flyer Templates --- Filming Equipment & Channels	Use / Improve Wiki --- Use / Improve Card Deck	Use / Improve Wiki --- Use / Improve Card Deck	Use / Improve Wiki --- Use / Improve Card Deck	Use / Improve Wiki --- Use / Improve Card Deck	Read posts and study documentation of last unClosing	Building Log & Manual
Admin and Costs																			Total € =	176450
Stakeholders

## Copy (5115) of 3 Year Planning
Anticipated Duration (Months)	Ongoing	0.25	1	4		0.5	?	0.5	1	1	3.5	6	6	5	1	0.5	Forever	Total =	30.25	and Forever
		PRE MONASTERY									THE CYCLES
	Development	Scoping	Pre-Mon Recon	Recruitment	Repairs & Refurb	Summit	Repairs & Refurb	Startup	Uncivilisation Readjustment Therapy	Unopening	6 Months	12 Months	18 Months	24 Months	Unclosing	After Care	Follow Up
Journey	Who is taking leadership?	Would it work here?	Build a team, Go there, Make it Hardcore		Remember you'll be living here	Establish Critical Mass. Put it through it's paces --- DDOS THE BUILDING --- Prime the Mortar for action and dicussion	Remember you'll be living here	unMon in a box will help you; good luck.	Learn to love and respect each other	Introduce yourselves and pray that people come					Burn success and publicly celebrate your mistakes	You have a responsibility to relationships formed.	Don't break the connection, go back.
COMMON / PUBLIC
Key Tasks / Objectives		Meet with partners & Build relationships --- Assess Location and Building According to framework --- Action Plan for Pre-Unmon Recon ---	Assemble Team, Equipment & Materials --- Host two Public Meetings --- Define Objectives --- Catalog in High Detail Building Faults --- Setup Website --- Establish Legals / Paperwork	Go headhunting --- Sculpt the call --- Establish unMonk criteria, decision making framework and pick --- Start learning the language	Repair it --- Who's paying? --- Order & fit unMon starter kit --- Connect utilities	Synthesise objectives into a meaningful event --- Invite people --- Involve locals	Repair it --- Who's paying? --- Order & fit unMon starter kit --- Connect utilities	Coordinate Arrival --- Source 1st Project Materials --- Get Kitchen / Food up and running	Alignment --- Agree Strategies --- Adopt Roles	Involve & Invite Locals into organising and participating at the unOpening --- Do the Event - Trust in the Process	Re-evaluate			Start handing over projects to local collaborators ---- Plan & Book return follow up	Schedule 1 week for group assesment of project --- Assign individual unMonks to important allies and friends, so to ensure relationship are maintained --- Plan unClosing	Be sure you leave the building better than you found it and in good clean standing --- Finalise Building Manual --- Manage with care the hand over procedure	Continue to invite energy & network resource into whatever the building has become ---- Send delegation on 6 month cycles, to visit and feast --- Continue remote calls with allies & friends
Communication		Weekly Community Calls	Weekly Community Calls	Weekly Community Calls	Weekly Community Calls	Weekly Community Calls	Weekly Community Calls	Weekly Community Calls
The Work		DELIVERABLE: Scoping Report ---	DELIVERABLE: Building Report & Proposed Fixes --- Building Rituals	Intiate and convey expectations --- DELIVERABLE: Attract talented minds and interest to the unMonastery		DELIVERABLE: Mobilise local networks --- DELIVERABLE: Bring an international conversation and expertise --- Refine, change and delete projects with respect to place.		Deciding existing projects to fork	Establish Routine
The Network

BACKSTAGE
Personal Wellbeing								Rescue missions from civilisation - Arrival & Returning
The Building & Utilities		Assess Multiple Buildings --- Research Utilities	Log Building Report & Begin Repairs --- Map Building in 3D --- Photograph building		Install Open Energy Monitor	Structure Hackathon sessions around repairing the building --- Plan first iteration of the layout	Install Open Energy Monitor	Fit unMonk Kits --- Establish a prioritised plan for building improvement & systems --- Finish fitout		Create Map & walk through of unOpening Event	Reassess use of building ---- Maintain Clean Living Standards ---- Continue Improvements ---- Keep track of resources	Reassess use of building ---- Maintain Clean Living Standards ---- Continue Improvements ---- Keep track of resources	Reassess use of building ---- Maintain Clean Living Standards ---- Continue Improvements ---- Keep track of resources	Reassess use of building ---- Maintain Clean Living Standards ---- Continue Improvements ---- Keep track of resources ---- Pay Final Bills		Finanlise Building Log and Manual
unMon in a Box		Scoping Report Framework / Document Template --- unMon Scoping Kit	Building Report Framework --- Building Scoping Kit	Application Form --- unMonastery website & network --- Talking Pieces	Building Report --- Building Log & Manual	LOTE unConference Planner --- Harmonious Hackathon Framework --- Twitterstorm --- unMonastery website & network	Building Report --- Building Log & Manual	Use Card Deck --- Use Wiki --- Read the Book of Mistakes	Read about Sleeping Arrangements	Website --- Poster & Flyer Templates --- Filming Equipment & Channels	Use / Improve Wiki --- Use / Improve Card Deck	Use / Improve Wiki --- Use / Improve Card Deck	Use / Improve Wiki --- Use / Improve Card Deck	Use / Improve Wiki --- Use / Improve Card Deck	Read posts and study documentation of last unClosing	Building Log & Manual
Admin and Costs	H&S Course €? --- Development Coordinator €4500 ---	Pre-Mon Development Costs (e.g. travel, per diems etc.) €2500	Legal €4000 --- Pre-Mon Recon Team Travel & Per Piems €6000		unMon Startup furniture €3000? --- OEM €150 --- Utilities ?? --- Travel €350 / unMonk --- Insurance €2500	Summit €6000	unMon Startup furniture €3000? --- OEM €150 --- Utilities ?? --- Travel €350 / unMonk --- Insurance €2500	Travel €350 / unMonk --- unMonasterian Starter Kit €600 / unMonk? --- Startup costs e.g. projectors, tech, plates etc. €4000			unAbbots €2000 ---- unMonks €400 / month --- Internet etc €80 --- Printing €80 --- Equipment €120 --- Abbot Travel €300	unAbbots €2000 ---- unMonks €400 / month --- Internet etc €80 --- Printing €80 --- Equipment €120 --- Abbot Travel €300	unAbbots €2000 ---- unMonks €400 / month --- Internet etc €80 --- Printing €80 --- Equipment €120 --- Abbot Travel €300	unAbbots €2000 ---- unMonks €400 / month --- Internet etc €80 --- Printing €80 --- Equipment €120 --- Abbot Travel €300				Total € =	176450
Stakeholders
											34680

## Timeline 2015-17
	2015					2016					2017
	March	April	May	June	July	August	September	October	November	December	January	February	March	April	May	June	July	August	September	October	November	December	January	February	March	April	May	June	July	August	September	October	November	December
unMonastery MetaNational
Events
PreSummit			1-4th
unSummit			???
Performing Encounters		17th
HTWT London / Chisenhale			14th
NearNow Cities Event					24th - 27th
OSCE Days				11th - 15th
Uckermark Happening
OuiShare			20th - 22nd
OpenState
Chaos Camp					13th-17th
BIOS Lunch Summit
BIOS
Beta Development
Scriptorium
Protocol
BoM
Web tools
Beta Release				@OSCE???	NearNow???
Version 1.0 Development
Version 1.0 Release					CHRISTMAS?
Arts Council Funding					Report
Pro Helvetia Funding (not confirmed)		Decision			Valencia		Bio Commons Summit	Nottingham	Bergen
ORG Development
Iteration V1.0
Board Meeting / unSummit			???	???
Iteration V2.0
Board Meeting					@UCKERMARK?
Iteration V3.0
Board Meeting					???
Iteration V4.0
Board Meeting
Athens
Key Events in the City
Adhocracy
ITM Community Action Network
Ideas City Athens
OSCE Days				11th - 15th
ADAF (Athens Digital Arts Fest)			21-24th
Innovating Privacy		3-4th
Commons Fest Athens		17-18th
Hybrid City Conf. "Data to the People"					17-19th
Datajournalism Hackathon	28-29th

Documenta 14
unMonastery Phased Development
Scoping
Networks and Partners
Recon
Recruitment
Repairs and Refurb
Summit
Startup
unOpening

Uckermark
unMonastery Phased Development
Scoping
Networks and Partners
Recon
Recruitment
Repairs and Refurb
Summit
Startup
Matera
unMonastery Phased Development
Outcome of Matera Election