## OVERALL MAZI TIMELINE
	2016					2017					2018
	January	February	March	April	May	June	July	August	September	October	November	December	January	February	March	April	May	June	July	August	September	October	November	December	January	February	March	April	May	June	July	August	September	October	November	December
	M1	M2	M3	M4	M5	M6	M7	M8	M9	M10	M11	M12	M13	M14	M15	M16	M17	M18	M19	M20	M21	M22	M23	M24	M25	M26	M27	M28	M29	M30	M31	M32	M33	M34	M35	M36
MAZI Events					MAZI toolkit v0.1
				MAZI Berlin Workshop
				Inura Conference Bucharest
				London Workshop
				MAZI toolkit v0.2
				1st MAZI Summer School
				Zurich Workshop
				2nd MAZI summer school
				MAZI v3
				Edinburgh Festival
MAZI BERLIN
Phase 0 - Project Setup
Phase 1 - Co-design Framework / lo-fi prototyping
Phase 2 - Creating information base
Phase 3 - Input/Co-creating
Phase 4 - Synthesis, Expert Evaluation and Filtering
Phase 5 – Developing Scenarios / Community Academy
Phase 6 – Public Debate
Phase 7 - Evaluation / Dissemination
MAZI Deptford
Phase 1 – Community engagement process
Phase 2 – Initial implementation
Phase 3 - Integrated MAZI trial
Phase 4 - Final MAZI toolkit trial
MAZI Kraftwerk1
Phase 1 - Observation
Phase 2 – MAZI offering
Phase 3 – Implementation and evaluation
Phase 4 – Evaluation and Documentation
MAZI UnMonastary
Phase 1 - Setting up an unMonastery
Phase 2a – Running of an unMonastery
Phase 3 – Decamping/Handover of an unMonastery
Phase 4 – unMonastery Summit

## unMonastery Working Timeline
	2016					2017					2018
	NO MAZI DELIVERABLES					Phase 1 - Setting up unMon				Phase 2a and 2b - Running unMonastery					Phase 3 - Wrap up		Phase 4 - unSummit
	January	February	March	April	May	June	July	August	September	October	November	December	January	February	March	April	May	June	July	August	September	October	November	December	January	February	March	April	May	June	July	August	September	October	November	December
	M1	M2	M3	M4	M5	M6	M7	M8	M9	M10	M11	M12	M13	M14	M15	M16	M17	M18	M19	M20	M21	M22	M23	M24	M25	M26	M27	M28	M29	M30	M31	M32	M33	M34	M35	M36
Key unMonastery Happenings
BIOS Launch - V1.0 Beta
Spring Gathering (UK)
unSummit #2 (Greece)
Autumn Gathering (Matera?)
Winter Gathering (???)
Sping Gathering (???)
unSummit #3 (??)
Autumn Gathering (???)
Winter Gathering (???)
Key unMonastery Organ Developments
Finalise AoA
Complete Company House Registerations
Reconcile all digital assets
Put in place basic infrastructure for timebank & decision making
Host first AGM
Review timebank
????
????
????
????
MAZI unMonastary (EXISTING TIMELINE) w/ Deliverables Added
MAZI toolkit v0.1					MAZI toolkit v0.1
Phase 1 - Setting up an unMonastery
During this phase the pilot will capture data of individual unMonasterians' interaction to help write the Protocol (recording the mechanics of the unMonastery community)					Report on deliverable
MAZI toolkit v0.2					MAZI toolkit v0.2
Phase 2a – Running of an unMonastery
A variety of pop-up urban interventions using the MAZI toolkit will be tried out to forge local connections, by forecasting our activities in the house, in the city, and globally.					Report on deliverable
Phase 2b Fostering mid-term and long-term relationship with the city and its citizens
During phase the MAZI toolkit will be used to introduce the unMonastery group and its goals to the local community and foster mid-term and long-term relationships.					Report on deliverable
Finally, we will build a community around unMonastery work in the cityneighbourhood to make sure the projects have real long-term value (measuring our contributions to the commons)					Report on deliverable
MAZI Toolkit v3					MAZI Toolkit v3
Phase 3 – Decamping/Handover of an unMonastery
Before handing over the location to local forces, the pilot will document the community outreach activities for the BGLO and establish the means to keep in touch with stakeholders, including the invisible stakeholders.					Report on deliverable
Phase 4 – unMonastery Summit
A coming together of the wider community in Edinburgh to organise and participate in Liquid City Festival, in collaboration with Edinburgh Napier University.					Report on deliverable
The unMonastery kiosk will visualize all data that was captured and the beautiful relationships that have been built using the MAZI toolkit and enriched the unMonastery Atlas (Visual unMonastery Analytics)					Report on deliverable
MAZI Events					MAZI toolkit v0.1
				MAZI Berlin Workshop
				Inura Conference Bucharest
				London Workshop
				MAZI toolkit v0.2
				1st MAZI Summer School
				Zurich Workshop
				2nd MAZI summer school
				MAZI v3
				Edinburgh Festival

## Budget
Just sketching very rough numbers here!		for later ref

1 Month of unMonastery (based on 3 people coming and going)					1 Month of unMonastery Urban Satielite					1 Month of unMonastery W/ unAbbot Model (based on 3 people coming and going)
Item	Units	Unit Cost	Cost		Item	Units	Unit Cost	Cost		Item	Units	Unit Cost	Cost
unMonasterians Per Diem	8	€400.00	€3,200.00		unMonasterians Per Diem	3	€400.00	€1,200.00		unMonasterians Per Diem	8	€400.00	€3,200.00
Travel Grants Per Month	3	€300.00	€900.00		Travel Grants Per Month	1	€300.00	€300.00		Travel Grants Per Month	3	€300.00	€900.00
Project Materials	1	€300.00	€300.00		Project Materials	1	€150.00	€150.00		Project Materials	1	€300.00	€300.00
Utilities	1	€150.00	€150.00		Utilities	1	€75.00	€75.00		Utilities	1	€150.00	€150.00
Service costs	1	€50.00	€50.00		Rental	1	€500.00	€500.00		Service costs	1	€50.00	€50.00
			€0.00					unAbbott	1	€1,500.00	€1,500.00

Total			€4,600.00		Total			€2,225.00		Total			€6,100.00
12 Month Total			€55,200.00		12 Month Total			€26,700.00		12 Month Total			€73,200.00
21 Month Total (based on Gantt)			€96,600.00		21 Month Total (based on Gantt)			€46,725.00		21 Month Total (based on Gantt)			€128,100.00

End of MAZI event deliverables					unMon Start up costs					Travel grants for public dissemination of the work
Item	Units	Unit Cost	Cost		Item	Units	Unit Cost	Cost		Item	Units	Unit Cost	Cost
					Furniture & Appliances	1	€5,000.00	€5,000.00		Travel grant	1	€300.00	€300.00
					Refurbishment	1	€4,000.00	€4,000.00		Accomodation	1	€150.00	€150.00
					Hardware and Equipment	1	€3,000.00	€3,000.00		Per Diem (assumes 3 days)	1	€60.00	€60.00
					Insurance	1	€1,000.00	€1,000.00

					Total			€13,000.00		Total			€510.00
							Total for 25			€12,750.00

## Numbers
unMonastery MAZI numbers
Type	Amount	Justification
Personnel	32,000
Overheads	19,000
Travel	18,000	For participation in project plenary meetings, EC review meetings, dissemination, and exploitation planning activities (including workshop,s conferences, summits, industrial presentations).
Equipment	6,000	Depreciation of DIY equipment for the pilot.
Consumables	0
Subcontracting	0
Other	20,000	For the organisation and implementation of the unMonastery pilot.
Total	95,000
Funding	95,000